## cmdList
Command #	Command Name	Frequent	Config File	Variable	Test-2006/11/26	Hawaii Status	Okay? -- Test Day 1	Ryan's Okay	Okay? -- Test Day 2	Comments Day 1	Jeff's New Comments Day 2	Ryan's Fixes/Comments
001	TAIL_MESSAGES		N/A	N/A	Sent 4:08	Need to check TM. Operator must type leading zeros (e.g. 001)	NO	YES	YES – almost	Type 001 NOT 1 to execute. Where does “last X lines of /var/log/messages (1-1000, -1 to cancel)” get sent?	Tested by watching /tmp/tail_messages on flight computer. Need to check file sent over telemetry	Creates a file /tmp/tail_messages sends file in telemetry
002	TAIL_ANITA		N/A	N/A		Need to check TM.	not tested	YES	YES – almost	Type 002 NOT 2 to execute. Test??	Tested by watching /tmp/tail_anita.log on flight computer. Need to check file sent over telemetry	Creates a file /tmp/tail_anita sends file in telemetry
003	CMD_START_NEW_RUN	YES	N/A	N/A		OK	YES	YES	YES	Type 003 NOT 3 to execute.	Tested by watching new created directory on /mnt/blade/
129	CMD_SHUTDOWN_HALT		N/A	N/A		OK	YES	YES	YES	Tested by watching shutdown in console.	Tested by watching shutdown in console.
130	CMD_REBOOT	YES	N/A	N/A	Under heavy load, took a few minutes. Ryan will add a kill of acqd and monitord.	No test.	not tested	not tested
131	CMD_KILL_PROGS		N/A	N/A	deferred	OK	YES	YES	YES	Tested by killing Acqd	Killed all progs and checked top on flight computer
132	CMD_RESPAWN_PROGS	YES	N/A	N/A	Tested with GPSd, verified in logs. SIPd needs to catch and execute own restart.			YES		Not sure how to test
133	CMD_START_PROGS		N/A	N/A	deferred	OK	YES	YES	YES	Tested by starting Acqd. Does stoping and starting Acqd start a new RUN#	Tested by using option 12 and checking processes on flight computer
134	CMD_MOUNT		N/A	N/A	deferred	No test.	not tested	not tested
135	CMD_WHITEHEAT		N/A	N/A	deprecated	No test.	not tested	not tested
136	CMD_MOUNT_NEXT_USB		anitaSoft.config	bladeName	tried by hand to fix missing ext USB	No test.	not tested	not tested
137	CMD_MOUNT_NEXT_BLADE		anitaSoft.config	usbIntName, usbExtName	deferred	No test.	not tested	not tested
138	CMD_EVENT_DISKTYPE		anitaSoft.config	eventDiskBitMask, hkDiskBitMask	deferred	OK	not tested	not tested	YES		Tested by enabling Hockey Brick and watching “df”
139	CMD_HK_DISKTYPE		anitaSoft.config	eventDiskBitMask, hkDiskBitMask	deferred	OK	not tested	not tested	YES		Tested by enabling Hockey Brick and checking “lsof |grep gps
140	ARCHIVE_STORAGE_TYPE		anitaSoft.config	eventDiskBitMask, hkDiskBitMask	deferred	No test.	not tested	not tested
141	ARCHIVE_PRI_DISK				deferred	No test.	not tested	not tested
142	ARCHIVE_PRI_ENC_TYPE				deferred	No test.	not tested	not tested
143	ARCHIVE_ALTERNATE_USB				deferred	No test.	not tested	not tested
144	ARCHIVE_DECIMATE_PRI				deferred	No test.
145	ARCHIVE_DEFAULT_FRAC				deferred	No test.				not implemented in flightsoft
146	TELEM_TYPE				deferred	No test.	not tested	not tested
147	TELEM_PRI_ENC_TYPE				deferred	No test.	not tested	not tested
148	ARCHIVE_PPS_PRIORITIES				deferred	No test.
149	ARCHIVE_PPS_DECIMATE				deferred	No test.
150	CMD_TURN_GPS_ON		Calibd.config	stateGPS	sent at 2:59 saw magnetometer activity	OK	NO	YES	YES	Can not check since “off” command doesn't work	Tested by monitoring ADU5 PPS on scope and by checking config file	Can't test voltages remotely
151	CMD_TURN_GPS_OFF		Calibd.config	stateGPS	sent at 2:50-noGPS times seen in events	OK	NO	YES	YES	GPS seems to update data after command is sent.	Tested by monitoring ADU5 PPS on scope and by checking config file	Can't test voltages remotely
152	CMD_TURN_RFCM_ON	YES	Calibd.config	stateRFCM[1-4]	Works by hand, but not with cmdsend	OK	YES	YES	YES	Tested with AnitaViewer. RFCM's were off then toggled on. This worked once but seems flaky. RFCM's did not come on after a reboot and this command would not start them either.	Tested by checking config file and by monitoring current on +40V power supply.	Can't test voltages remotely
153	CMD_TURN_RFCM_OFF	YES	Calibd.config	stateRFCM[1-4]	Works by hand, but not with cmdsend.	OK	YES	YES	YES	Tested with AnitaViewer. RFCM's were on then toggled off. Another flaky command.	Tested by checking config file and by monitoring current on +40V power supply.	Can't test voltages remotely
154	CMD_TURN_CALPULSER_ON	YES	Calibd.config	stateCalPulser	OK	OK	NO	YES	YES	Originally came one with output 1 pulsing but now nothing happens.	Tested by checking config file and by monitoring signal on scope.	Can't test voltages remotely
155	CMD_TURN_CALPULSER_OFF	YES	Calibd.config	stateCalPulser	OK	OK	NO	YES	YES	Can not test since pulser will not come back on	Tested by checking config file and by monitoring signal on scope.	Can't test voltages remotely
156	CMD_TURN_VETO_ON	YES	Calibd.config	stateVeto	OK	OK	NO	YES	YES	No voltage observed on pins A & B of VETO 1 & 2 connector on RFCM filter pin boxes. When executed command prints “Really turn on Noise Diode”.	Tested by checking +12V on pins A & B on VETO 1 & 2 connectors on RFCM filter pin boxes and by confirming config file change.	Can't test voltages remotely
157	CMD_TURN_VETO_OFF	YES	Calibd.config	stateVeto	OK	OK	NO	YES	YES	Could not turn on so VETO off could not be properly tested. When executed command prints “Really turn off Noise Diode”.	Tested by checking +12V on pins A & B on VETO 1 & 2 connectors on RFCM filter pin boxes and by confirming config file change.	Can't test voltages remotely
158	CMD_TURN_ALL_ON	YES	Calibd.config	stateGPS, stateRFCM[1-4], stateCalPulser, stateVeto	OK	OK	NO	YES	YES	Flags stay set on “1” so change from 0 – 1 could not be observed. Also, executed command prints “Really turn on GPS, RFCM, CalPulsr and ND”.	Tested by monitoring +12V on VETO 1, current on +40V power supply, ADU5 PPS and CalPulser port 1 signal on scope simultaneously. Also verified in config file.	Can't test voltages remotely
159	CMD_TURN_ALL_OFF		Calibd.config	stateGPS, stateRFCM[1-4], stateCalPulser, stateVeto	OK	OK	NO	BUG –Fixed	YES	Changes flags in Calibd.config to “1” instead of “0”. Also, when command is executed it prints “Really turn off GPS, RFCM, CalPulser and ND”.	Tested by monitoring +12V on VETO 1, current on +40V power supply, ADU5 PPS and CalPulser port 1 signal on scope simultaneously. Also verified in config file.	Can't test voltages remotely
171	SET_CALPULSER_SWITCH		Calibd.config	steadyState	OK	OK	NO	Should Work	BUG-Fixed	Can not test since pulser will not come back on	Tested by monitoring Calibd.config and watching waveforms on scope (all 4 ports and loop mode)	Can't test voltages remotely
172	SET_CALPULSER_ATTEN		Calibd.config	attenLoop, attenStartState	OK	OK	NO	Should Work	BUG-Fixed	Text for command prints “Set Sun Sensor gain to”. What are the attenuation values for 0-7?	Tested by monitoring Calibd.config and watching waveforms on scope (checked a few attenuation values and testing attenuation loop mode)	Can't test voltages remotely
173	CP_ATTEN_LOOP_PERIOD				OK	OK	not tested	not tested	YES		Changed from 2s to 10s and observed change in config file and on scope
174	CP_SWITCH_LOOP_PERIOD				OK	OK	not tested	not tested	YES		Changed from 1000 to 3s and observed change on scope and in config file
175	CP_OFF_LOOP_PERIOD				OK	OK	not tested	not tested	YES		Changed from 1000 to 0s and observed change on scope and in config file.
176	SET_CALIB_WRITE_PERIOD						not tested	not tested
180	SET_ADU5_PAT_PERIOD		GPSd.config	patPeriod	OK	OK	NO	BUG – Fixed	YES	Observed no change in GPSd.config (patPeriod) when changing from 1s to 5s.	Changes in GPSd.config
181	SET_ADU5_SAT_PERIOD		GPSd.config	satPeriod	OK		YES	YES	NO	Changed from 600s to 700s and back to 600s. Works fine.	Observed no change in GPSd.config when changing period from 400s to 500s.
182	SET_G12_PPS_PERIOD	YES	GPSd.config	ppsPeriod	500	OK	YES	YES	YES	Changed from 200ms to 40ms and back to 200ms. Works fine.	Observed changes from 200ms to 300ms in GPSd.config
183	SET_G12_PPS_OFFSET	YES	GPSd.config	ppsOffset	150	OK	NO	BUG – Fixed	YES	Tried changing from 50ms to 100ms but no change was observed in GPSd.config (ppsOffset)	Observed changes from 100.5ms to 200.5ms in GPSd.config
184	ADU5_CAL_12		GPSd.config	calibV12_[1-3]	Tested by Kim	No test.	not tested	not tested
185	ADU5_CAL_13		GPSd.config	calibV13_[1-3]	Tested by Kim	No test.	not tested	not tested
186	ADU5_CAL_14		GPSd.config	calibV14_[1-3]	Tested by Kim	No test.	not tested	not tested
187	ADU5_VTG_PERIOD		GPSd.config		BAD	No test.
188	G12_POS_PERIOD		GPSd.config		Position period in ms, not 100 ms as in cmdsend	No test.
190	SET_HK_PERIOD		Hkd.config	readoutPeriod	OK	No test.	NO	BUG – Fixed		Changed from 10 to 20 but observed no change in Hkd.config (readoutPeriod)
191	SET_HK_CAL_PERIOD		Hkd.config	calibrationPeriod	OK	No test.	NO	BUG – Fixed		Changed from 60s to 30s but observed on change in Hkd.config (calibrationPeriod)
195	SIPD_SEND_WAVE		Sipd.config		Sent by hand	No test.
196	SIPD_THROTTLE_RATE		Sipd.config		Sent by hand	No test.
197	SIPD_PRIORITY_BANDWIDTH		Sipd.config		BUG	No test.
198	LOSD_PRIORITY_BANDWIDTH		Losd.config		BUG	No test.
199	LOSD_SEND_DATA		Losd.config		Sent by hand	No test.
200	CLEAN_DIRS		N/A	N/A		No test.	not tested	not tested
210	SEND_CONFIG		Selectable	N/A		No test.	not tested	not tested
211	DEFAULT_CONFIG		Selectable	N/A		No test.	not tested	not tested
212	SWITCH_CONFIG		Selectable	N/A		No test.	not tested	not tested
213	LAST_CONFIG		Selectable			No test.
220	MONITORD_RAMDISK_KILL_ACQD		Monitord.config			No test.
221	MONITORD_RAMDISK_DUMP_DATA		Monitord.config			No test.
222	MONITORD_MAX_ACQD_WAIT		Monitord.config			No test.
223	MONITORD_PERIOD		Monitord.config			No test.
224	MONITORD_USB_THRESH		Monitord.config			No test.
225	MONITORD_BLADE_THRESH		Monitord.config			No test.
226	MONITORD_MAX_QUEUE		Monitord.config			No test.
230	ACQD_ADU5_TRIG_FLAG	YES	Acqd.config	enablePPS1Trigger		High rate	not tested	not tested	PROBLEMS		Confirmed in Acqd.config and by monitoring trig type in AnitaViewer. Observed 40-50Hz event rate when enabled
231	ACQD_G12_TRIG_FLAG	YES	Acqd.config	enablePPS2Trigger		High rate	not tested	not tested	PROBLEMS		Checked Acqd.config and monitored event rate on Ryan's Header Plots. (+ AnitaViewer). Observed 40-50Hz event rate when enabled.
232	ACQD_SOFT_TRIG_FLAG		Acqd.config	sendSoftTrigger		BAD	not tested	not tested	NO		No change observed in Acqd.config
233	ACQD_SOFT_TRIG_PERIOD		Acqd.config	softTrigSleepPeriod		No test.	not tested	not tested
234	ACQD_ENABLE_CHAN_SERVO	YES	Acqd.config	enableChanServo		No test.	not tested	not tested
235	ACQD_SET_PID_GOAL	YES	Acqd.config	pidGoal		OK	YES	YES	YES	Tested by changing from 2400 to 2500 and back to 2400.	Checked Acqd.config and monitored scalar rates with TrigMon to confirm 2.5 Mhz global rate
236	ACQD_PEDESTAL_RUN		Acqd.config	pedestalMode		No test.	not tested	not tested
237	ACQD_THRESHOLD_SCAN		Acqd.config	doThresholdScan		Check termination	NO	BUG – Fixed		Can not disable threshold scan after enabling. Data does not seem to be correct for plotting threshold scan.
238	SET_ANT_TRIG_MASK	YES	Acqd.config	antTrigMask		Not tested	not tested	not tested
239	SET_SURF_TRIG_MASK		Acqd.config	surfTrigBandMask		OK	YES	YES	YES	Changed all to 0. Works but very confusing how to mask trigger bands.	Masked and unmasked overlapping frequency bands on SHORTs 28-31 successfully
240	SET_GLOBAL_THRESHOLD		Acqd.config	setGlobalThreshold, globalThreshold		Can't disable SetGlobalThreshold flag	NO	YES		globalThreshold in Acqd.config gets set (tested by changing from 10 to 25 and back to 10) but setGlobalThreshold flag in Acqd.config gets stuck on 1. Needs disable option.		Setting the threshold to 0 disables it. Modified cmd to print this on screen.
241	ACQD_REPROGRAM_TURF		Acqd.config	reprogramTurf		No test.	not tested	not tested
242	SURFHK_PERIOD		Acqd.config	surfHkPeriod		No test.	not tested	not tested
243	SURFHK_TELEM_EVERY		Acqd.config	surfHkTelemEvery		No test.	not tested	not tested
244	TURFHK_TELEM_EVERY		Acqd.config	turfHkTelemEvery		No test.	not tested	not tested
245	NUM_PED_EVENTS		Acqd.config	numPedEvents		No test.	not tested	not tested
246	THRESH_SCAN_STEP_SIZE		Acqd.config	thresholdScanStepSize		No test.	NO	BUG – Fixed		Tried changing from 40 to 60 but observed no change in Acqd.config.
247	THRESH_SCAN_REPEAT		Acqd.config	thresholdScanPointPerStep		No test.	not tested	BUG – Fixed
248	CHAN_PID_GOAL_SCALE BAND_SCALE_FACTOR		Acqd.config			No test.
249	ACQD_SET_RATE_SERVO		Acqd.config			No test.
250	ACQD_SET_NICE_VALUE		Acqd.config	Tested 'by hand'. Must respawn to take effect.		No test.
251	EVENTD_MATCH_GPS		Eventd.config			No test.
253	PRIORITIZERD_COMMAND	YES	Prioritizerd.config			No test.				see second sheet

## Prioritzerd
Prioritizer Subcommands of Command 253

NAME	Number	Variable
PRI_HORN_THRESH	1	hornThresh	1
PRI_HORN_DESC_WIDTH	2	hornDiscWidth	1
PRI_HORN_SECTOR_WIDTH	3	hornSectorWidth	1
PRI_CONE_THRESH	4	coneThresh	1
PRI_CONE_DESC_WIDTH	5	coneDiscWidth	1
PRI_HOLDOFF	6	holdoff	1
PRI_DELAY	7	delay	1
PRI_HORN_GUARD_OFFSET	8	hornGuardOffset	1
PRI_HORN_GUARD_WIDTH	9	hornGuardWidth	1
PRI_HORN_GUARD_THRESH	10	hornGuardThreshold	1
PRI_CONE_GUARD_OFFSET	11	coneGuardOffset
PRI_CONE_GUARD_WIDTH	12	coneGuardWidth
PRI_CONE_GUARD_THRESH	13	coneGuardThresh
PRI_FFT_PEAK_MAX_A	14	FFTPeakMaxA	1
PRI_FFT_PEAK_MAX_B	15	FFTPeakMaxB	1
PRI_FFT_PEAK_WINDOW_L	23	FFTPeakWindowL	1
PRI_FFT_PEAK_WINDOW_R	24	FFTPeakWindowR	1
PRI_FFT_MAX_CHANNELS	22	FFTMaxChannels	1
PRI_RMS_MAX	16	RMSMax
PRI_RMS_EVENTS	17	RMSevents
PRI_WINDOW_CUT	18	WindowCut
PRI_BEGIN_WINDOW	19	BeginWindow
PRI_END_WINDOW	20	EndWindow
PRI_METHOD_MASK	21	MethodMask	1